## Sprint
Backlog Item | Task | Task Owner | Total Story Points | S1 | S2 | S3 | S4 | S5 | S6 | S7
|  |  |  | 2021-12-03 | 2021-03-22 | 2021-04-01 | 2021-04-12 | 2021-04-23 | 2021-05-03 | 2021-05-14
|  |  |  | 256 | 249 | 199 | 149 | 99 | 49 | 11 | Ideal Burndown
|  |  | 12 | 256 | 249 | 221 | 198 | 126 | 38 | 0 | Remaining Hrs (Total)
Team Formation and Project Management Setup | Decide on Tech stats | All | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Requirement Analysis and Discussion | All | 3 | 3 | 0 | 0 | 0 | 0 | 0
Plan and Strategize overall design | Design Architecture | All | 3 | 3 | 0 | 0 | 0 | 0 | 0
| Design and Create Database schema, tables | Vamsi | 12 | 12 | 12 | 12 | 9 | 3 | 0
| Businsess Logic and Design finalization | All | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Design UI Wireframes | Kevin, Tejas | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Finalize implemenation workload based on features | All | 2 | 2 | 2 | 0 | 0 | 0 | 0
Early development and environment readiness | Develop Frontend Code Base | Kevin, Tejas | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Develop Backend Code Base | Vamsi, Shreshta | 5 | 5 | 5 | 0 | 0 | 0 | 0
OnlineBanking Fontend Development | Develop UI for Admin functionalities - Frontend | Kevin | 6 | 6 | 6 | 6 | 0 | 0 | 0
| Develop UI for Customer Core functionalities - Frontend | Shreshta | 7 | 7 | 7 | 7 | 3 | 3 | 0
| Develop UI for Payments functionalities - Frontend | Shreshta | 33 | 33 | 33 | 33 | 30 | 15 | 0
| Develop UI for Transfer functionalities - Frontend | Shreshta | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Develop UI for Add Refund functionalities - Frontend | Kevin | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Develop UI for Applications functionalities - Frontend | Kevin | 14 | 14 | 14 | 14 | 14 | 11 | 0
| Develop UI for Account approval functionalities - Frontend | Kevin | 3 | 3 | 3 | 3 | 3 | 3 | 0
OnlineBanking Backend Development | Design REST APIs for Admin functionalities - Backend | Vamsi | 17 | 17 | 17 | 17 | 12 | 8 | 0
| Design REST APIs for Customer Core functionalities - Backend | Vamsi | 9 | 9 | 9 | 9 | 4 | 1 | 0
| Design REST APIs for Bill Payements functionalities - Backend | Shreshta | 26 | 26 | 26 | 26 | 23 | 6 | 0
| Desgin REST APIs for Fund Transfers functionalities - Backend | Vamsi | 4 | 4 | 4 | 4 | 4 | 0 | 0
| Design REST APIs for Customer SignUp functionality - Backend | Shreshta | 10 | 10 | 10 | 10 | 7 | 0 | 0
| Design REST APIs for Applications functionalities - Backend | Vamsi | 15 | 15 | 15 | 15 | 15 | 4 | 0
| Deploy Backend on AWS EC2, staging, prod environments | Tejas | 3 | 3 | 3 | 3 | 3 | 0 | 0
Testing | Test OnlineBanking Backend APIs on staging and prod environments | Tejas | 22 | 22 | 22 | 22 | 22 | 22 | 0
| Test OnlineBanking Application on staging and prod environments | Tejas | 10 | 10 | 10 | 10 | 10 | 10 | 10
Documentation | Maintain artifacts and related documentation | All | 28 | 28 | 28 | 28 | 28 | 28 | 28
Total Story Points : 256 Sprint 1 is shortest and warm sprint, so estimated to deliver 7 points Sprint 2: 50 Sprint 3 : 50 Sprint 4: 50 Sprint 5: 50 Sprint 6: 50